## Milestones v2
Type | Title | Start date | End date | Duration (in days)
Task | Brainstorm Ideas | 2019-10-09 | 2019-10-23 | 15
Task | Draft Aims & Objectives | 2019-10-16 | 2019-11-01 | 17
Milestone | Project Idea Chosen | 2019-11-01 | 2019-11-01 | -
Task | Draft the Literature Review | 2019-11-01 | 2019-11-14 | 14
Task | Presentation Preparation | 2019-11-01 | 2019-11-14 | 14
Milestone | Basic Documentation Complete | 2019-11-08 | 2019-11-08 | -
Task | Setup Work Environment | 2019-11-08 | 2019-11-11 | 4
Milestone | Perform Mock Interim Discussion | 2019-11-14 | 2019-11-14 | -
Task | Interim Discussion Preparation | 2019-11-14 | 2019-12-06 | 23
Task | Software Requirements Specification | 2019-11-14 | 2019-12-13 | 30
Task | Create Calibration Scene in Unity (Control) | 2019-11-14 | 2019-12-06 | 23
Task | Draft Design Work | 2019-11-22 | 2019-12-06 | 15
Task | Draft Risk Assessment Table | 2019-11-22 | 2019-12-06 | 15
Task | Sort out 3D Models/Avatars | 2019-11-29 | 2019-12-20 | 22
Task | Design the Main Menu Screen | 2019-11-29 | 2019-12-06 | 8
Milestone | Interim Discussion Presentation | 2019-12-06 | 2019-12-06 | -
Task | Script/code the Main Menu Screen | 2019-12-06 | 2019-12-13 | 8
Task | Design/Layout Scene 1 | 2019-12-13 | 2019-12-20 | 8
Task | Script the Objects in Scene 1 | 2019-12-20 | 2020-01-17 | 29
Milestone | Main Scripts & Scene 1 complete | 2020-01-17 | 2020-01-17 | -
Task | Prepare for Alpha Test | 2020-01-17 | 2020-01-31 | 15
Task | Create Feedback Forms | 2020-01-17 | 2020-01-31 | 15
Task | Test Scene 1 | 2020-01-17 | 2020-01-31 | 15
Milestone | Alpha Test | 2020-01-31 | 2020-01-31 | -
Task | Adapt Application using Feedback | 2020-01-31 | 2020-02-07 | 8
Task | Modify Risk Assessment Table | 2020-01-31 | 2020-02-07 | 8
Task | Design/Layout Scene 2 | 2020-02-07 | 2020-02-10 | 4
Task | Script the Objects in Scene 2 | 2020-02-10 | 2020-02-21 | 12
Task | Test Scene 2 | 2020-02-21 | 2020-02-24 | 4
Task | Design/Layout Scene 3 | 2020-02-24 | 2020-02-28 | 5
Task | Script the Objects in Scene 3 | 2020-02-28 | 2020-03-07 | 9
Task | Book People for Main Experiment | 2020-03-06 | 2020-03-11 | 6
Task | Advertise Main Experiment | 2020-03-06 | 2020-03-11 | 6
Task | Test Scene 3 | 2020-03-07 | 2020-03-11 | 5
Milestone | Main Experiment | 2020-03-11 | 2020-03-11 | -
Task | Record Results into Tables/Graphs | 2020-03-11 | 2020-03-13 | 3
Task | Draft Discussion/Conclusion | 2020-03-13 | 2020-03-24 | 12
Milestone | Draft Report Submission | 2020-03-24 | 2020-03-24 | -
Milestone | Code finalised | 2020-04-10 | 2020-04-10 | -
Task | Additional Testing & Data Collection | 2020-04-10 | 2020-04-17 | 8
Task | Design/Create Video Presentation | 2020-04-17 | 2020-05-01 | 15
Task | Finalise Risk Assessment | 2020-04-24 | 2020-05-01 | 8
Milestone | Implementation Demostration | 2020-05-01 | 2020-05-01 | -
Milestone | Final Draft of Dissertation | 2020-05-15 | 2020-05-15 | -
Milestone | Final Submission | 2020-05-26 | 2020-05-26 | -