## Project Management Plan
Type | Title | Start date | End date | Duration (in days)
Task | Brainstorm Ideas | 2019-10-09 | 2019-10-23 | 11
Task | Create Project Outline, Aims & Objectives | 2019-10-16 | 2019-11-01 | 13
Milestone | Project Idea Chosen | 2019-11-01 | 2019-11-01 | -
Task | Do Literature Review & Presentation Preparation | 2019-11-01 | 2019-11-14 | 10
Milestone | Project Aims, Objectives & Milestones complete | 2019-11-08 | 2019-11-08 | -
Task | Setup Unity Project & GitHub Repository | 2019-11-08 | 2019-11-11 | 2
Milestone | Perform Mock Interim Discussion | 2019-11-14 | 2019-11-14 | -
Task | Interim Discussion Preparation | 2019-11-14 | 2019-11-29 | 12
Task | Key Design (UML diagrams, sketches, etc.) | 2019-11-22 | 2019-12-06 | 11
Milestone | Interim Discussion Presentation | 2019-11-29 | 2019-11-29 | -
Task | Create and acquire the main 3D models needed | 2019-11-29 | 2019-12-20 | 16
Task | Coding in Unity | 2019-11-29 | 2020-04-24 | 106
Milestone | Main Object programming & scripts complete | 2020-01-10 | 2020-01-10 | -
Task | Prepare for Alpha test (practice experiment) & bug fixing | 2020-01-10 | 2020-01-31 | 16
Task | Create Feedback Forms | 2020-01-17 | 2020-01-31 | 11
Milestone | Alpha Test | 2020-01-31 | 2020-01-31 | -
Task | Adapt/Fix Experiment & Application based on feedback | 2020-02-03 | 2020-03-06 | 25
Task | Book room & time-slots for Experiment | 2020-03-06 | 2020-03-09 | 2
Task | Advertise main experiment and book people | 2020-03-09 | 2020-03-18 | 8
Milestone | Main Experiment (Beta) | 2020-03-18 | 2020-03-18 | -
Task | Record Results into tables & graphs | 2020-03-18 | 2020-03-23 | 4
Milestone | Draft Report Submission | 2020-03-24 | 2020-03-24 | -
Milestone | Code finalised | 2020-04-24 | 2020-04-24 | -
Task | Window for Additional Testing & Data Collection | 2020-04-24 | 2020-05-15 | 16
Milestone | Final Draft of Dissertation | 2020-05-15 | 2020-05-15 | -
Milestone | Final Submission | 2020-05-26 | 2020-05-26 | -