## Import Tasks
Task List | Task | Description | Assignee | Due Date | Start Date
Task | Brainstorm Ideas | Come up with lots of project ideas | jw01324@surrey.ac.uk | 2019-10-23 | 2019-10-09
Task | Draft Aims & Objectives | Outline the Aims & Objectives | jw01324@surrey.ac.uk | 2019-11-01 | 2019-10-16
Milestone | Project Idea Chosen | Finalise project idea | jw01324@surrey.ac.uk | 2019-11-01 | 2019-11-01
Task | Draft the Literature Review | Find sources & put in context of project | jw01324@surrey.ac.uk | 2019-11-14 | 2019-11-01
Milestone | Basic Documentation Complete | Aims, objectives & milestones | jw01324@surrey.ac.uk | 2019-11-08 | 2019-11-08
Task | Setup Work Environment | GitHub repository & Unity project | jw01324@surrey.ac.uk | 2019-11-11 | 2019-11-08
Milestone | Perform Mock Interim Discussion | Presentation with supervisor | jw01324@surrey.ac.uk | 2019-11-14 | 2019-11-14
Task | Interim Discussion Preparation | Diagrams & updated PowerPoint | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-14
Task | Draft Design Work | UML diagrams, sketches, key decisions | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-22
Milestone | Interim Discussion Presentation | Complete the interim presentation | jw01324@surrey.ac.uk | 2019-12-06 | 2019-12-06
Task | Sort out 3D Models/Avatars | Create, or aquire models with permission | jw01324@surrey.ac.uk | 2019-12-20 | 2019-11-29
Milestone | Main Scripts & Scene 1 complete | Scene 1 done for alpha test | jw01324@surrey.ac.uk | 2020-01-17 | 2020-01-17
Task | Prepare for Alpha Test | Practice experiment & organise testers | jw01324@surrey.ac.uk | 2020-01-31 | 2020-01-17
Task | Create Feedback Forms | VRSQ/SSQ or custom Questionnaire | jw01324@surrey.ac.uk | 2020-01-31 | 2020-01-17
Milestone | Alpha Test | Perform alpha test on friends/family | jw01324@surrey.ac.uk | 2020-01-31 | 2020-01-31
Task | Adapt Application using Feedback | Fix mistakes & possibly rethink designs | jw01324@surrey.ac.uk | 2020-02-07 | 2020-01-31
Task | Book People for Main Experiment | Rooms, times, days, etc. | jw01324@surrey.ac.uk | 2020-03-11 | 2020-03-06
Task | Advertise Main Experiment | Social media & students | jw01324@surrey.ac.uk | 2020-03-11 | 2020-03-06
Milestone | Main Experiment | All data collected by this date | jw01324@surrey.ac.uk | 2020-03-11 | 2020-03-11
Task | Record Results into Tables/Graphs | Demographics, data, results, etc. | jw01324@surrey.ac.uk | 2020-03-13 | 2020-03-11
Milestone | Draft Report Submission | Submit a full draft of the dissertation | jw01324@surrey.ac.uk | 2020-03-24 | 2020-03-24
Milestone | Code finalised | All programming finished by this date | jw01324@surrey.ac.uk | 2020-04-10 | 2020-04-10
Task | Additional Testing & Data Collection | Window for additonal testing with final app | jw01324@surrey.ac.uk | 2020-04-17 | 2020-04-10
Milestone | Final Draft of Dissertation | Submit the finished dissertation | jw01324@surrey.ac.uk | 2020-05-15 | 2020-05-15
Milestone | Final Submission | Submit the application and video | jw01324@surrey.ac.uk | 2020-05-26 | 2020-05-26
Task | Design the Main Menu Screen | Key functionality (Start, Exit, etc.) | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-29
Task | Script/code the Main Menu Screen | Links to scenes 1, 2, & 3 | jw01324@surrey.ac.uk | 2019-12-13 | 2019-12-06
Task | Design/Layout Scene 1 | Place prefabs and proportion models | jw01324@surrey.ac.uk | 2019-12-20 | 2019-12-13
Task | Script the Objects in Scene 1 | Object scripts & triggers for the scenario | jw01324@surrey.ac.uk | 2020-01-17 | 2019-12-20
Task | Test Scene 1 | Bug testing and design flaw checks | jw01324@surrey.ac.uk | 2020-01-31 | 2020-01-17
Task | Design/Layout Scene 2 | Place prefabs and proportion models | jw01324@surrey.ac.uk | 2020-02-10 | 2020-02-07
Task | Script the Objects in Scene 2 | Object scripts & triggers for the scenario | jw01324@surrey.ac.uk | 2020-02-21 | 2020-02-10
Task | Test Scene 2 | Bug testing and design flaw checks | jw01324@surrey.ac.uk | 2020-02-24 | 2020-02-21
Task | Design/Layout Scene 3 | Place prefabs and proportion models | jw01324@surrey.ac.uk | 2020-02-28 | 2020-02-24
Task | Script the Objects in Scene 3 | Object scripts & triggers for the scenario | jw01324@surrey.ac.uk | 2020-03-07 | 2020-02-28
Task | Test Scene 3 | Bug testing and design flaw checks | jw01324@surrey.ac.uk | 2020-03-11 | 2020-03-07
Task | Draft Risk Assessment Table | Risk assessment initially | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-22
Task | Modify Risk Assessment Table | Risk assessment after alpha finished | jw01324@surrey.ac.uk | 2020-02-07 | 2020-01-31
Task | Finalise Risk Assessment | Risk assessment in the final weeks | jw01324@surrey.ac.uk | 2020-05-01 | 2020-04-24
Task | Software Requirements Specification | SRS document outlining plan | jw01324@surrey.ac.uk | 2019-12-13 | 2019-11-14
Task | Presentation Preparation |  | jw01324@surrey.ac.uk | 2019-11-14 | 2019-11-01
Task | Create Test Scene in Unity | Basic show of how the app will look/act | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-14
Task | Draft Discussion/Conclusion | Comparing results to literature data, etc. | jw01324@surrey.ac.uk | 2020-03-24 | 2020-03-13
Task | Design/Create Video Presentation | Video presentation on the application | jw01324@surrey.ac.uk | 2020-05-01 | 2020-04-17
Milestone | Implementation Demostration | Feedback on implementation | jw01324@surrey.ac.uk | 2020-05-01 | 2020-05-01
Task | Create Calibration Scene (Control) | Coding simple reaction time test | jw01324@surrey.ac.uk | 2019-12-06 | 2019-11-14